Project Planning Phase

Project Planning Template

This academic project-planning document defines the backlog, sprint schedule, estimation approach, progress tracker, velocity calculation, and burndown method for an automation project using FLOW DESIGNER.

| Project Information | Details |
| --- | --- |
| Date | 28.09.2026 |
| Team ID | SWTID-2026-4440 |
| Project Name | Auto Ticket Classification using FLOW DESIGNER |
| Maximum Marks | 5 Marks |

Project Scope and Expected Outcome

The project will design and implement an automation workflow that classifies incoming support tickets using their available content and configured classification rules. The workflow is expected to apply category, subcategory, and priority information, route each ticket to the correct support group, and provide a manual-review path for cases with low classification confidence.

The expected outcome is a documented and testable FLOW DESIGNER automation with traceable classification results. The project will also provide evidence for testing and reporting, including classification accuracy, routing success, exception handling, and deployment readiness.

Product Backlog, Sprint Schedule, and Estimation

The following product backlog divides the project into four coherent epics and assigns realistic story points, priorities, and team responsibilities. The planned backlog contains 80 story points across four six-day sprints.

| Sprint | Functional Requirement (Epic) | User Story Number | User Story / Task | Story Points | Priority | Team Members |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint-1 | Data Preparation and Ticket Taxonomy | USN-1 | As a project analyst, I can define ticket categories and classification rules so that incoming requests have a consistent taxonomy. | 3 | High | Team Member 1; Team Member 2 |
| Sprint-1 | Data Preparation and Ticket Taxonomy | USN-2 | As a project analyst, I can collect or import historical support-ticket data for analysis and labeling. | 5 | High | Team Member 1; Team Member 2 |
| Sprint-1 | Data Preparation and Ticket Taxonomy | USN-3 | As a data preparer, I can clean and normalize ticket subject, description, priority, and requester fields. | 5 | High | Team Member 1; Team Member 2 |
| Sprint-1 | Data Preparation and Ticket Taxonomy | USN-4 | As a project team, I can label a representative sample of tickets against the agreed categories and rules. | 5 | High | Team Member 1; Team Member 2 |
| Sprint-1 | Data Preparation and Ticket Taxonomy | USN-5 | As a project team, I can document taxonomy decisions and acceptance criteria for later testing. | 2 | Medium | Team Member 1; Team Member 2 |
| Sprint-2 | Flow Designer Classification Workflow | USN-6 | As a support process owner, I can trigger the workflow when a new support ticket is created. | 3 | High | Team Member 1; Team Member 2 |
| Sprint-2 | Flow Designer Classification Workflow | USN-7 | As a support process owner, I can classify tickets using ticket content and configured classification rules. | 8 | High | Team Member 1; Team Member 2 |
| Sprint-2 | Flow Designer Classification Workflow | USN-8 | As a support process owner, I can set category, subcategory, priority, and assignment group values from the classification result. | 5 | High | Team Member 1; Team Member 2 |
| Sprint-2 | Flow Designer Classification Workflow | USN-9 | As a support process owner, I can apply confidence handling and send uncertain classifications to a defined fallback path. | 3 | High | Team Member 1; Team Member 2 |
| Sprint-2 | Flow Designer Classification Workflow | USN-10 | As a project team, I can record the classification result and relevant decision details for traceability. | 1 | Medium | Team Member 1; Team Member 2 |
| Sprint-3 | Review, Routing, and Notifications | USN-11 | As a support agent, I can review and correct a ticket classification before or after routing when required. | 5 | High | Team Member 1; Team Member 2 |
| Sprint-3 | Review, Routing, and Notifications | USN-12 | As a support process owner, I can route classified tickets to the correct queue or support team. | 5 | High | Team Member 1; Team Member 2 |
| Sprint-3 | Review, Routing, and Notifications | USN-13 | As a support process owner, I can notify agents or requesters when a classification or routing update requires communication. | 3 | Medium | Team Member 1; Team Member 2 |
| Sprint-3 | Review, Routing, and Notifications | USN-14 | As a project team, I can log exceptions and failed classifications so that unresolved cases can be investigated. | 5 | High | Team Member 1; Team Member 2 |
| Sprint-3 | Review, Routing, and Notifications | USN-15 | As a support agent, I can preserve the original ticket details while applying approved classification and routing updates. | 2 | Medium | Team Member 1; Team Member 2 |
| Sprint-4 | Testing, Reporting, and Deployment | USN-16 | As a tester, I can create a representative test set covering categories, priorities, routing outcomes, and fallback cases. | 3 | High | Team Member 1; Team Member 2 |
| Sprint-4 | Testing, Reporting, and Deployment | USN-17 | As a project team, I can measure classification accuracy and routing success against defined acceptance criteria. | 5 | High | Team Member 1; Team Member 2 |
| Sprint-4 | Testing, Reporting, and Deployment | USN-18 | As a project owner, I can view a monitoring or summary view of classifications, corrections, exceptions, and routing results. | 5 | High | Team Member 1; Team Member 2 |
| Sprint-4 | Testing, Reporting, and Deployment | USN-19 | As a project team, I can document and publish the approved workflow, operating steps, and known limitations. | 2 | Medium | Team Member 1; Team Member 2 |
| Sprint-4 | Testing, Reporting, and Deployment | USN-20 | As a project owner, I can deploy the workflow and prepare a handover checklist for continued use and review. | 5 | High | Team Member 1; Team Member 2 |

Project Tracker, Velocity & Burndown Chart

The tracker below provides a planned six-day schedule beginning after the planning date. Students should update completed story points and actual release dates as each sprint is executed.

| Sprint | Total Story Points | Duration | Sprint Start Date | Sprint End Date (Planned) | Story Points Completed (as on Planned End Date) | Sprint Release Date (Actual) |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint-1: Preparation | 20 | 6 Days | 17 February 2025 | 22 February 2025 | To be updated | To be updated |
| Sprint-2: Workflow Build | 20 | 6 Days | 24 February 2025 | 1 March 2025 | To be updated | To be updated |
| Sprint-3: Validation and Routing | 20 | 6 Days | 3 March 2025 | 8 March 2025 | To be updated | To be updated |
| Sprint-4: Testing and Deployment | 20 | 6 Days | 10 March 2025 | 15 March 2025 | To be updated | To be updated |
| Planned Total | 80 | 24 Days | — | — | To be updated | To be updated |

Velocity

Velocity measures the amount of completed work delivered by the team during a sprint. In this project, it is based on completed story points for the FLOW DESIGNER classification workflow rather than on the number of tickets processed.

Velocity formulas Average daily velocity = total completed story points ÷ sprint duration in days. Worked example: for a six-day sprint with 20 completed story points, average daily velocity = 20 ÷ 6 = 3.33 story points per day. Average sprint velocity = total completed story points ÷ number of completed sprints.

For example, if the team completes 20 story points in each of two completed sprints, the average sprint velocity is (20 + 20) ÷ 2 = 20 story points per sprint. The values should be recalculated after actual sprint completion because unfinished, added, or re-estimated work can change the result.

Use the measured velocity to support planning for later sprints. It should guide discussion and forecasting, not be used to pressure the team into an artificial target.

Burndown Chart

A burndown chart is a graphical representation of the work remaining over time. For this project, it can show whether the remaining story points for a sprint are decreasing at a rate that supports completion of the classification workflow and its related testing activities.

The following sample assumes a 20-point sprint completed over six days. The ideal values provide a reference line, while the actual values must be entered from the team's daily progress record.

| Day | Ideal Remaining Work | Actual Remaining Work |
| --- | --- | --- |
| Day 0 | 20 | To be updated |
| Day 1 | 16.7 | To be updated |
| Day 2 | 13.3 | To be updated |
| Day 3 | 10 | To be updated |
| Day 4 | 6.7 | To be updated |
| Day 5 | 3.3 | To be updated |
| Day 6 | 0 | To be updated |

How to convert the sample into a chart

- Update the Actual Remaining Work column at the end of each day using the story points that remain unfinished.

- Select the Day, Ideal Remaining Work, and Actual Remaining Work columns in the document or a spreadsheet.

- Insert a line chart with Day on the horizontal axis and remaining story points on the vertical axis.

- Compare the actual line with the ideal line and record any causes of delay, scope change, or early completion.

The chart should compare ideal remaining work with actual remaining work. It should not be treated as evidence of completion until the daily actual values have been entered and reviewed.

Reference

The following references are retained from the planning template and may be consulted for Agile estimation, sprint planning, epics, and burndown-chart preparation.

- https://www.visual-paradigm.com/scrum/scrum-burndown-chart/

- https://www.atlassian.com/agile/tutorials/burndown-charts

- https://www.atlassian.com/agile/project-management

- https://www.atlassian.com/agile/tutorials/how-to-do-scrum-with-jira-software

- https://www.atlassian.com/agile/tutorials/epics

- https://www.atlassian.com/agile/tutorials/sprints

- https://www.atlassian.com/agile/project-management/estimation